DOMINUS GRAY, LLC

CMMC Engagement Playbook

Standard Operating Procedure for CMMC Level 2 Compliance Assessments

Prepared By: Dominus Gray, LLC

Date: February 2026

Version: 1.0

Classification: INTERNAL USE ONLY

— CONFIDENTIAL —

# Purpose & Scope

This playbook defines the end-to-end process for delivering CMMC Level 2 compliance engagements. It covers pre-sales through remediation support and C3PAO preparation. Every consultant delivering CMMC services must follow this playbook to ensure consistent, high-quality client outcomes.

ℹ Applicability This playbook applies to all CMMC Level 2 (Advanced) readiness assessments, gap analyses, and remediation advisory engagements. For Level 1 (Foundational) self-assessments, use the abbreviated process in Appendix A.

# Engagement Lifecycle Overview

Every CMMC engagement follows six phases:

| Phase | Duration | Key Activities | Exit Criteria |
| --- | --- | --- | --- |
| 1. Pre-Sales & Scoping | 1–2 weeks | Discovery call, scoping questionnaire, proposal | Signed SOW & NDA |
| 2. Kickoff & Data Collection | 1–2 weeks | Kickoff meeting, document request, system inventory | Completed intake package |
| 3. Assessment Execution | 3–6 weeks | Control-by-control assessment, interviews, evidence review | All 110 controls assessed |
| 4. Analysis & Deliverable Assembly | 1–2 weeks | SPRS scoring, gap analysis, remediation roadmap | Draft deliverables reviewed |
| 5. Remediation Advisory | 4–12 weeks | POA&M tracking, implementation guidance, policy development | All POA&M items addressed |
| 6. C3PAO Preparation | 2–4 weeks | Mock assessment, evidence binder review, readiness check | Client ready for C3PAO |

# Phase 1: Pre-Sales & Scoping

## 1.1 Discovery Call

Objective: Qualify the opportunity, understand the client's CUI environment, and determine engagement scope.

Discovery Call Agenda (30–60 minutes):

- Introductions and Dominus Gray capabilities overview (5 min)

- Client's current compliance posture and motivations (10 min)

- CUI data types and flow discussion (10 min)

- System boundary and technology environment overview (10 min)

- Timeline and budget constraints (5 min)

- Next steps and scoping questionnaire (5 min)

## 1.2 Scoping Questionnaire

Send the scoping questionnaire within 24 hours of the discovery call. The following information is required to develop an accurate proposal:

| Category | Information Required | Why It Matters |
| --- | --- | --- |
| Company Profile | Legal name, CAGE code, DUNS, size standard, SDVOSB/HUBZone status | Contract eligibility and SPRS registration |
| Contract Landscape | Active/pending DoD contracts, prime vs. sub, CUI marking guide | Determines scope and urgency |
| CUI Environment | Types of CUI handled, data flows, storage locations | Defines system boundary |
| IT Infrastructure | On-prem vs. cloud, endpoints, network topology, mobile devices | Assessment complexity and control applicability |
| Current Policies | Existing SSP, policies, incident response plan, training records | Baseline maturity assessment |
| Personnel | Employee count, IT staff, security personnel, cleared personnel | Interview scheduling and access control scope |
| Prior Assessments | Previous NIST 800-171 assessments, DIBCAC audits, SPRS score | Starting point for gap analysis |
| Timeline | Contract deadlines, C3PAO target date, fiscal year constraints | Engagement planning |

## 1.3 Proposal Development

Develop the proposal using the standard Dominus Gray SOW template. Every proposal must include:

- Executive summary of client's compliance challenge

- Scope of work with explicit inclusions and exclusions

- Deliverables list (SSP, POA&M, Gap Assessment at minimum)

- Engagement timeline with milestone dates

- Team composition and qualifications

- Fixed-fee pricing (preferred) or T&M estimate with cap

- Terms referencing the Dominus Gray MSA

⚠ Pricing Guidance Standard CMMC L2 readiness assessment: $15,000–$45,000 depending on scope. Do not quote below $12,000 — it signals commodity service and attracts price-only buyers. Add $5,000–$10,000 for remediation advisory. Get managing director approval for any engagement under $15,000.

## 1.4 Pre-Engagement Checklist

| Item | Status | Notes |
| --- | --- | --- |
| NDA executed | ☐ | Use standard Dominus Gray Mutual NDA template |
| SOW signed | ☐ | Ensure scope explicitly lists deliverables |
| Payment terms established | ☐ | 50% upfront, 50% on delivery (standard) |
| Initial payment received | ☐ | Do not begin work before deposit clears |
| Client POC identified | ☐ | Technical and executive sponsors |
| Document request list sent | ☐ | Use standard document request template |
| Engagement folder created | ☐ | Standard folder structure in secure storage |
| Kick-off meeting scheduled | ☐ | Within 5 business days of signed SOW |

# Phase 2: Kickoff & Data Collection

## 2.1 Kickoff Meeting

Required attendees: Client executive sponsor, IT lead, security lead (if separate), Dominus Gray engagement lead, technical assessor.

Kickoff Agenda (90 minutes):

- Welcome and team introductions (10 min)

- CMMC 2.0 overview and what Level 2 means for the client (15 min)

- Engagement scope review and timeline confirmation (10 min)

- System boundary definition workshop (20 min)

- Document request review and assignment (15 min)

- Interview schedule planning (10 min)

- Communication plan and status reporting cadence (10 min)

✓ Key Outcome The client must leave the kickoff meeting with a clear understanding of what CUI they handle, where it resides, and what the system boundary includes. If they cannot answer these questions, schedule a follow-up CUI scoping session before proceeding.

## 2.2 Document Request List

Request the following documentation within the first week:

| Document | Control Families Supported | Priority |
| --- | --- | --- |
| Network architecture diagram | SC, CA, AC | Critical |
| Asset inventory / CMDB | CM, SC, MP | Critical |
| Existing security policies | All families | Critical |
| System Security Plan (if any) | All families | Critical |
| Access control lists / user directory | AC, IA | High |
| Incident response plan (if any) | IR | High |
| Vulnerability scan reports (last 90 days) | RA, SI | High |
| Training records | AT | High |
| Physical security documentation | PE | Medium |
| Maintenance records | MA | Medium |
| Media handling/sanitization procedures | MP | Medium |
| Backup and recovery procedures | CP (if applicable) | Medium |
| Vendor/subcontractor list | SR (TPRM) | Medium |
| Previous assessment reports | CA | Low |

## 2.3 CUI Scoping & System Boundary

Proper scoping is the most critical step of the engagement. An incorrectly scoped boundary leads to inaccurate assessments and potential C3PAO failures.

Scoping Process:

- Step 1 — Identify CUI: Review contract clauses (DFARS 252.204-7012), DD Form 254, CUI marking guides. Identify what CUI is received, created, stored, processed, and transmitted.

- Step 2 — Map Data Flows: Document how CUI enters the environment, where it moves, where it's stored, and how it exits. Include email, file shares, cloud services, and mobile.

- Step 3 — Define Boundary: Draw the logical and physical boundary around all systems that process, store, or transmit CUI. This becomes the scope of the SSP.

- Step 4 — Identify Out-of-Scope Systems: Explicitly document systems excluded from scope and the justification (no CUI contact).

- Step 5 — Document Interconnections: Identify all connections crossing the boundary — internet, VPN, APIs, cloud services, vendor connections.

⚠ Common Scoping Mistakes Watch for: email systems excluded when CUI is sent via email, personal devices accessing CUI through webmail, cloud services like OneDrive/SharePoint containing CUI but not in scope, subcontractor systems receiving CUI. Each of these must be in the boundary or explicitly controlled.

# Phase 3: Assessment Execution

## 3.1 Control Assessment Methodology

Assess all 110 NIST 800-171 Rev 2 security requirements across the 14 control families. For each control, determine one of three statuses:

| Status | SPRS Points | Definition | Evidence Required |
| --- | --- | --- | --- |
| MET | Full value | Control is fully implemented as described in 800-171 | Documentation + demonstrated implementation |
| NOT MET | Deduct value | Control is not implemented or only partially implemented | Document the gap and current state |
| NOT APPLICABLE | Full value | Control does not apply to the system (rare — must justify) | Written justification |

## 3.2 Assessment Techniques

Use a combination of techniques for each control:

- Examine: Review policies, procedures, system configurations, screenshots, logs

- Interview: Speak with personnel responsible for implementing the control

- Test: Where possible, verify control operation (access attempts, scans, configuration checks)

ℹ Evidence Standards Evidence must demonstrate that the control is both implemented and operational. A policy alone is not sufficient — you must see evidence that the policy is enforced. Screenshots should include timestamps. Configuration exports are preferred over screenshots where available.

## 3.3 Control Family Assessment Guide

For each of the 14 control families, use this guide to structure your assessment:

| Family | ID | Controls | Key Interview Targets | Critical Evidence |
| --- | --- | --- | --- | --- |
| Access Control | AC | 22 | IT Admin, System Admins | ACLs, user lists, MFA configs, remote access logs |
| Awareness & Training | AT | 3 | HR, Training Coordinator | Training records, completion certificates, curricula |
| Audit & Accountability | AU | 9 | IT Admin, SIEM Admin | Audit logs, SIEM dashboards, retention policies |
| Configuration Management | CM | 9 | IT Admin, Change Manager | Baselines, change logs, software inventory |
| Identification & Authentication | IA | 11 | IT Admin, Help Desk | Password policies, MFA enrollment, account management |
| Incident Response | IR | 3 | Security Lead, IT Manager | IR plan, incident logs, exercise records |
| Maintenance | MA | 6 | IT Admin, Facilities | Maintenance logs, remote maintenance tools, approvals |
| Media Protection | MP | 9 | IT Admin, Office Manager | Encryption configs, sanitization logs, media tracking |
| Personnel Security | PS | 2 | HR, Security Officer | Background check records, termination procedures |
| Physical Protection | PE | 6 | Facilities, Security Guard | Access logs, visitor logs, camera footage |
| Risk Assessment | RA | 3 | ISSO, Management | Risk assessment report, vulnerability scans |
| Security Assessment | CA | 4 | ISSO, IT Manager | Previous assessments, POA&Ms, continuous monitoring |
| System & Communications | SC | 16 | Network Admin, IT Admin | Firewall rules, encryption configs, network diagrams |
| System & Info Integrity | SI | 7 | IT Admin, AV Admin | AV/EDR configs, patch logs, monitoring alerts |

## 3.4 Interview Protocol

Before each interview:

- Send a brief agenda and list of topics 2+ business days in advance

- Review relevant documentation already collected

- Prepare control-specific questions (do not just read the control text)

During the interview:

- Explain the purpose — this is not an audit, it's a readiness assessment to help them succeed

- Ask open-ended questions: "Walk me through how a new user gets access to [system]"

- Request live demonstrations where appropriate ("Can you show me the MFA enrollment screen?")

- Document the response, who provided it, and the date

- Note any follow-up evidence needed

After each interview:

- Summarize findings within 24 hours while details are fresh

- Send follow-up evidence requests within 48 hours

- Update the control assessment tracker

# Phase 4: Analysis & Deliverable Assembly

## 4.1 SPRS Score Calculation

Calculate the SPRS score using the DoD methodology:

- Start at 110 (perfect score)

- For each NOT MET control, subtract the weighted value per DoD Assessment Methodology v1.2.1

- Minimum score is -203

- A score of 110 means all controls are MET

⚠ CMMC Conditional Certification Rules Under CMMC 2.0 Final Rule (32 CFR Part 170): A contractor may receive conditional certification if their score is 88/110 or above (80%). Each NOT MET control in the POA&M must be no more than 1 point. All POA&M items must be remediated within 180 days. If these conditions are not met, the contractor cannot receive even conditional certification.

## 4.2 Deliverable Checklist

Every CMMC engagement produces the following minimum deliverables:

| Deliverable | Template | Owner | Review Required |
| --- | --- | --- | --- |
| CMMC Gap Assessment Report | cmmc-gap-assessment-template.docx | Lead Assessor | Peer review + client review |
| System Security Plan (SSP) | ssp-template.docx | Lead Assessor | Peer review + client sign-off |
| Plan of Action & Milestones (POA&M) | poam-template.docx | Lead Assessor | Client review + milestone dates |
| Executive Summary Briefing | PowerPoint (custom) | Engagement Lead | Managing Director review |

## 4.3 Quality Assurance Review

Before delivering any document to the client:

- All [PLACEHOLDER] text replaced with client-specific information

- All consultant instruction blocks deleted

- SPRS score calculation verified independently

- Control statuses cross-referenced with evidence

- Client name, system name, and dates consistent across all documents

- Formatting and branding consistent with Dominus Gray standards

- Spell check and grammar review completed

- Peer reviewer sign-off obtained

✓ Peer Review Requirement No deliverable leaves Dominus Gray without a peer review. The reviewer must be a different consultant than the one who performed the assessment. The reviewer checks for accuracy, completeness, consistency, and professional quality.

# Phase 5: Remediation Advisory

## 5.1 Remediation Planning

After delivering the gap assessment, guide the client through remediation:

- Prioritize by risk: Address controls with the highest SPRS point deductions first

- Group by effort: Bundle quick wins (policy updates, configuration changes) for early momentum

- Identify dependencies: Some controls depend on infrastructure changes that take time

- Set realistic timelines: Align with the client's resources and the 180-day POA&M window

## 5.2 Common Remediation Activities

| Gap Category | Typical Remediation | Effort Level | DG Role |
| --- | --- | --- | --- |
| Missing policies | Draft and implement security policies | Low–Medium | Draft policies, client reviews/approves |
| Weak access controls | Implement MFA, review ACLs, enforce least privilege | Medium | Advisory + validation |
| No SIEM/logging | Deploy SIEM solution, configure log sources | High | Requirements + vendor selection guidance |
| Unencrypted CUI | Enable encryption at rest and in transit | Medium | Technical guidance |
| No incident response | Develop IR plan, conduct tabletop exercise | Medium | Draft IR plan + facilitate exercise |
| Missing training | Implement security awareness training program | Low | Curriculum guidance + tracking |
| Physical security gaps | Badge readers, visitor logs, camera systems | High | Requirements only (not physical install) |
| Network segmentation | Implement CUI enclave or VLAN segmentation | High | Architecture guidance |

## 5.3 Status Reporting

During remediation, provide bi-weekly status reports to the client:

- POA&M item status (open, in progress, completed, overdue)

- Updated SPRS score projection

- Upcoming milestones and deadlines

- Risks and blockers

- Recommendations for the next reporting period

# Phase 6: C3PAO Preparation

## 6.1 Pre-Assessment Readiness Check

Before the client engages a C3PAO, conduct a final readiness review:

| Readiness Item | Status | Notes |
| --- | --- | --- |
| All 110 controls have documented implementation descriptions | ☐ |  |
| SSP is complete, current, and signed by authorizing official | ☐ |  |
| POA&M items are closed or within 180-day window | ☐ |  |
| Evidence binder organized with one folder per control family | ☐ |  |
| SPRS score submitted to Supplier Performance Risk System | ☐ |  |
| Key personnel can articulate control implementations verbally | ☐ |  |
| Policies and procedures are published and accessible to staff | ☐ |  |
| Security awareness training completed and documented for all users | ☐ |  |
| Incident response plan tested via tabletop exercise | ☐ |  |
| Network diagram current and matches actual environment | ☐ |  |
| CUI marking and handling procedures in place | ☐ |  |
| Subcontractor flow-down requirements documented | ☐ |  |

## 6.2 Mock Assessment

Conduct a mock assessment that mirrors the C3PAO experience:

- Select 20–30 controls for deep-dive review (focus on historically weak areas)

- Conduct interviews with key personnel as the C3PAO would

- Review evidence as if seeing it for the first time

- Document any findings using C3PAO assessment language

- Debrief the client on strengths and areas needing last-minute attention

## 6.3 C3PAO Selection Guidance

Advise the client on selecting a C3PAO:

- Verify C3PAO authorization status on the Cyber AB marketplace

- Confirm assessors have relevant industry experience

- Request and check references from other DIB companies

- Clarify timeline and scheduling availability

- Understand the C3PAO's assessment methodology and communication style

⚠ Conflict of Interest Dominus Gray CANNOT serve as both the RPO (Registered Practitioner Organization) providing advisory services AND the C3PAO performing the certification assessment for the same client. This is a CMMC ecosystem rule. Always recommend independent C3PAOs.

# Appendix A: Engagement Tools & Templates

The following templates are available in the Dominus Gray consulting library:

| Template | Filename | When to Use |
| --- | --- | --- |
| CMMC Gap Assessment Report | cmmc-gap-assessment-template.docx | Phase 4 — Assessment results and recommendations |
| System Security Plan | ssp-template.docx | Phase 4 — Document control implementations |
| Plan of Action & Milestones | poam-template.docx | Phase 4/5 — Track gaps and remediation |
| Incident Response Plan | ir-plan-template.docx | Phase 5 — If client lacks an IR plan |
| TPRM Vendor Assessment | tprm-assessment-template.docx | Phase 5 — Assess subcontractor compliance |
| V-CISO Monthly Report | vciso-report-template.docx | Ongoing — If transitioning to V-CISO retainer |
| Mutual NDA | nda-template.docx | Phase 1 — Before sharing confidential info |
| Teaming Agreement | teaming-agreement-template.docx | Phase 1 — If teaming with a partner |

# Appendix B: SPRS Score Weights Reference

The DoD Assessment Methodology assigns the following point values to each control. Controls worth 5 points represent the most critical requirements:

| Weight | Count | Example Controls |
| --- | --- | --- |
| 5 points | ~15 controls | MFA (3.5.3), FIPS encryption (3.13.11), audit logging (3.3.1) |
| 3 points | ~30 controls | Least privilege (3.1.5), configuration baselines (3.4.1) |
| 1 point | ~65 controls | Logon banners (3.1.9), maintenance logging (3.7.2) |